## Risk Treatment Plan
NovaCart Technologies Pvt. Ltd. Information Security Risk Treatment Plan
Risk ID | Asset | Risk Description | Current Risk Level | Treatment Option | Treatment Action | Security Measure | Risk Owner | Target Date | Residual Likelihood | Residual Impact | Residual Risk Level | Treatment Status
RA-001 | Customer Database | Data breach due to weak access controls | Critical | Mitigate | Implement MFA and review database access permissions | MFA, RBAC, database encryption | IT Manager | 2026-09-30 | Medium | High | High | Planned
RA-002 | Transaction Database | SQL injection due to insecure input validation | High | Mitigate | Implement secure input validation and conduct application security testing | WAF, secure coding, input validation | IT Manager | 2026-10-15 | Low | High | Medium | Planned
RA-003 | Employee Records | Unauthorized access due to weak password practices | High | Mitigate | Enable MFA and perform periodic access reviews | MFA, password policy, access reviews | HR Manager | 2026-09-30 | Low | High | Medium | Planned
RA-004 | Product Database | Data corruption due to improper database permissions | Medium | Mitigate | Review database permissions and implement change approval | RBAC, change management | Operations Manager | 2026-10-31 | Low | Medium | Low | Planned
RA-005 | Financial Records | Ransomware attack due to outdated endpoint protection | Critical | Mitigate | Deploy EDR and strengthen backup procedures | EDR, antivirus, encrypted backups | Finance Manager | 2026-09-30 | Medium | High | High | Planned
RA-006 | Warehouse Management System | System failure due to lack of redundancy | High | Mitigate | Implement system redundancy and test recovery procedures | High availability, backups, recovery testing | Operations Manager | 2026-10-31 | Low | High | Medium | Planned
RA-007 | Customer Website | DDoS attack due to insufficient traffic filtering | High | Mitigate | Configure advanced DDoS protection and monitor traffic | AWS Shield, WAF, monitoring | IT Manager | 2026-09-30 | Low | High | Medium | Planned
RA-008 | Microsoft 365 Tenant | Phishing attack due to low employee security awareness | Critical | Mitigate | Conduct security awareness and phishing simulation training | Email filtering, awareness training, MFA | IT Manager | 2026-09-15 | Medium | High | High | Planned
RA-009 | AWS Infrastructure | Cloud misconfiguration due to incorrect IAM permissions | High | Mitigate | Review IAM permissions and perform regular cloud configuration assessments | IAM, least privilege, configuration monitoring | Cloud Administrator | 2026-09-30 | Low | High | Medium | Planned
RA-010 | Employee Laptops | Malware infection due to unpatched operating systems | High | Mitigate | Implement automated patch management and endpoint monitoring | EDR, antivirus, patch management | IT Manager | 2026-09-15 | Medium | Medium | Medium | Planned
RA-011 | Network Firewall | Firewall failure due to misconfigured rules | High | Mitigate | Review and test firewall rules regularly | Firewall rule review, change management | IT Manager | 2026-10-31 | Low | High | Medium | Planned
RA-012 | Core Switch | Network outage due to hardware failure | Medium | Mitigate | Replace aging hardware and implement health monitoring | Network monitoring, redundancy | IT Manager | 2026-11-30 | Low | High | Medium | Planned
RA-013 | VPN Gateway | Unauthorized remote access due to weak authentication | High | Mitigate | Enforce MFA for all VPN connections | MFA, VPN authentication, access control | IT Manager | 2026-09-15 | Low | High | Medium | Planned
RA-014 | Backup Server | Backup failure due to unmonitored backup jobs | High | Mitigate | Monitor backup jobs and perform regular recovery tests | Backup monitoring, recovery testing | IT Manager | 2026-10-31 | Low | High | Medium | Planned
RA-015 | Office Wi-Fi Network | Unauthorized access due to weak Wi-Fi credentials | Medium | Mitigate | Upgrade wireless security and rotate credentials periodically | WPA3, strong authentication | IT Manager | 2026-11-30 | Low | Medium | Low | Planned
RA-016 | Payment Gateway Integration | Payment fraud due to API security weaknesses | High | Mitigate | Conduct API security testing and strengthen authentication | API authentication, security testing | Finance Manager | 2026-10-31 | Low | High | Medium | Planned
RA-017 | Email System | Business email compromise through phishing emails | Critical | Mitigate | Implement email authentication and security awareness training | DMARC, DKIM, SPF, MFA | IT Manager | 2026-09-30 | Medium | High | High | Planned
RA-018 | Source Code Repository | Source code theft due to excessive permissions | High | Mitigate | Review repository permissions and enforce MFA | RBAC, MFA, access reviews | Development Manager | 2026-10-31 | Low | High | Medium | Planned
RA-019 | SSL Certificates | Certificate expiry due to lack of monitoring | Medium | Mitigate | Implement automated certificate monitoring and renewal | Certificate monitoring, automated renewal | IT Manager | 2026-09-30 | Rare | High | Medium | Planned
RA-020 | Security | Outdated documentation due to missed policy reviews | Medium | Mitigate | Establish scheduled policy reviews and version control | Document control, annual reviews | Information Security Team | 2026-10-31 | Unlikely | Medium | Low | Planned
RA-021 | Information Security Policy | Non-compliance due to lack of employee awareness | Medium | Mitigate | Conduct annual policy awareness training | Security awareness training, policy acknowledgement | Information Security Team | 2026-11-30 | Low | Medium | Low | Planned
RA-022 | Asset Register | Inaccurate asset inventory due to assets not being updated | Medium | Mitigate | Perform quarterly asset verification and reconciliation | Asset management, periodic reviews | Information Security Team | 2026-12-31 | Low | Medium | Low | Planned
RA-023 | Risk Register | Unidentified risks due to risks not being regularly reviewed | High | Mitigate | Conduct quarterly risk reviews and update the risk register | Risk assessment, management review | Information Security Team | 2026-10-31 | Low | High | Medium | Planned
RA-024 | Business Continuity Plan | Disaster recovery failure due to an untested recovery plan | Medium | Mitigate | Conduct annual disaster recovery exercises and update recovery procedures | Business continuity testing, recovery procedures | Information Security Team | 2026-12-31 | Rare | High | Medium | Planned
RA-025 | Customer Support System | Data leakage due to excessive agent permissions | High | Mitigate | Review support-user permissions and apply least privilege | RBAC, access reviews, least privilege | Customer Support Manager | 2026-10-31 | Low | High | Medium | Planned
RA-026 | CCTV System | Physical security failure due to camera malfunction | Low | Mitigate | Establish preventive maintenance and periodic camera testing | CCTV monitoring, maintenance schedule | Administration Manager | 2026-11-30 | Rare | Medium | Low | Planned
RA-027 | Server Room | Unauthorized physical access due to weak physical controls | Medium | Mitigate | Strengthen physical access controls and review access logs | Access cards, biometric controls, CCTV | Administration Manager | 2026-10-31 | Rare | High | Medium | Planned
RA-028 | Internet Connection | ISP outage due to single-provider dependency | High | Mitigate | Establish a secondary ISP connection and review service SLA | Redundant ISP, SLA | IT Manager | 2026-11-30 | Low | High | Medium | Planned
RA-029 | Employee ID Cards | Identity misuse due to lost or stolen ID cards | Low | Mitigate | Immediately deactivate lost cards and maintain an ID inventory | Access card management | HR Manager | 2026-09-30 | Rare | Medium | Low | Planned
RA-030 | External Backup Storage | Backup data loss due to improper storage handling | Medium | Mitigate | Perform regular backup integrity tests and verify storage security | Encryption, backup testing, access control | IT Manager | 2026-10-31 | Rare | High | Medium | Planned

## Treatment Options
NovaCart Technologies Pvt. Ltd. Risk Treatment Options
Treatment Option | Description
Mitigate | Implement security controls or other actions to reduce the likelihood or impact of the risk.
Accept | Formally acknowledge the risk when further treatment is not justified or the remaining risk is within the organization's tolerance.
Transfer | Shift some or all of the risk to another party through mechanisms such as insurance or contractual arrangements.
Avoid | Eliminate the activity, process, or condition that creates the risk.

## Residual Risk
NovaCart Technologies Pvt. Ltd. Residual Risk Summary
Risk ID | Current Risk Level | Treatment Option | Residual Likelihood | Residual Impact | Residual Risk Level
RA-001 | Critical | Mitigate | Medium | High | High
RA-002 | High | Mitigate | Low | High | Medium
RA-003 | High | Mitigate | Low | High | Medium
RA-004 | Medium | Mitigate | Low | Medium | Low
RA-005 | Critical | Mitigate | Medium | High | High
RA-006 | High | Mitigate | Low | High | Medium
RA-007 | High | Mitigate | Low | High | Medium
RA-008 | Critical | Mitigate | Medium | High | High
RA-009 | High | Mitigate | Low | High | Medium
RA-010 | High | Mitigate | Medium | Medium | Medium
RA-011 | High | Mitigate | Low | High | Medium
RA-012 | Medium | Mitigate | Low | High | Medium
RA-013 | High | Mitigate | Low | High | Medium
RA-014 | High | Mitigate | Low | High | Medium
RA-015 | Medium | Mitigate | Low | Medium | Low
RA-016 | High | Mitigate | Low | High | Medium
RA-017 | Critical | Mitigate | Medium | High | High
RA-018 | High | Mitigate | Low | High | Medium
RA-019 | Medium | Mitigate | Rare | High | Medium
RA-020 | Medium | Mitigate | Unlikely | Medium | Low
RA-021 | Medium | Mitigate | Low | Medium | Low
RA-022 | Medium | Mitigate | Low | Medium | Low
RA-023 | High | Mitigate | Low | High | Medium
RA-024 | Medium | Mitigate | Rare | High | Medium
RA-025 | High | Mitigate | Low | High | Medium
RA-026 | Low | Mitigate | Rare | Medium | Low
RA-027 | Medium | Mitigate | Rare | High | Medium
RA-028 | High | Mitigate | Low | High | Medium
RA-029 | Low | Mitigate | Rare | Medium | Low
RA-030 | Medium | Mitigate | Rare | High | Medium

## Legend
NovaCart Technologies Pvt. Ltd. Risk Treatment Plan Legend
Term | Description
Risk Treatment | Process of selecting and implementing actions to modify identified information security risks.
Mitigate | Reduce the likelihood and/or impact of a risk through security controls or other actions.
Accept | Formally acknowledge and retain the risk within the organization's risk tolerance.
Transfer | Share or shift risk to another party through contractual, insurance, or other arrangements.
Avoid | Eliminate the activity or condition that creates the risk.
Residual Risk | Risk remaining after planned treatment actions and controls are applied.
Risk Owner | Person responsible for managing and monitoring the risk.
Treatment Status | Current progress of the selected risk treatment action.